## ICRISAT
CENTRE NAME: |  | ICRISAT
AUDITORS: |  | Janny van Beem (QMS and Standards), Simon Linington (Standards)
AUDIT SCOPE: |  | Conservation--documentation audit
AUDIT DATE: |  | 26 April 2018 - 31 of August 2018
REPORT DATE: |  | 20 of July, 2018
AUDIT FINDINGS | [7 empty] | POST-AUDIT RESPONSE |  | Clearance Round 1 (Y/N) | COMMENTS | Clearance Round 2 (Y/N/NA) | COMMENTS | CLEARANCE DATE
Finding No. | Location/ Section | Clause and Source | Description of the finding | Proposed Improvement | Mandatory or Recommendation (M/R) | Evidence required (Y/N) | Evidence due date | Actions taken to address finding | Evidence provided (such as links, documents)
ICRISAT-2018-CONS-1 | Policy | Clause 3.3.1 QMS: Audit Guide and Clause List v1.6 | The QMS Audit Guide and Clause List states that "the genebank shall have policies regarding germplasm in its collections including criteria for acquisition, introduction into long-term storage, medium-term storage and temporary holdings, inactivation, reactivation, archiving, duplicates, distribution, safety duplication and availability. " The Conservation SOP does not adequately describe curation policies. | Submit the genebank's curation policies as a Related Document. The conservation policies should describe criteria for the introduction of accessions into long-term, medium-term and temporary storage (e.g., mandate, legal status, health status, quantity and viability/vigour thresholds, the intervals at which accessions are tested for viability/vigour, the actions when viability/vigour and inventory fall below thresholds, "de-materialization" (e.g., in the event of loss of an MLS accession), and the steps taken when duplicate accessions are identified). | M | Y | 2018-08-03 | ICRISAT Germplasm Conservation Policy document included in the SOP addressing the audit findings and the proposed improvement. | Revised SOP | Y | A draft of ICRISAT's conservation policies was submitted. Members of the Policy Module are working towards creating a collective policy document which will be shared among genebank managers by the end of 2018 . | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-2 | Introduction | QMS | The introduction section states that the genebank collection is composed of 126,830 accessions. The GENESYS Institution Report states that the genebank conserves 126,780 accessions. Numbers reported yearly in various sites (such as the genebank's website, GENESYS, ORT, Genebank Platform and SOPs) should be identical. | Confirm that the number of accessions and species reported yearly in the genebank's website, GENESYS, the Crop Trust Online Reporting Tool (ORT), the Genebank Platform and the Conservation SOP are exactly the same. Ensure that the genebank has a protocol in place to periodically update information across public and private websites. | M | Y | 2018-08-03 | Genebank database updated for GENESYS to reflect the information in SOP. The Genebank is developing timelines for periodically updating the information in the website. | Revised SOP | Y | Number of accessions in the CONS SOP and GENESYS coincides. Timelines for periodically updating information in GENESYS and other portals are being developed by June 2019 (personal communication). | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-3 | Procedure | Clause 4.2.2, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "after drying, all seed samples shall be sealed in a suitable airtight container for storage". Step 6.1.6.1 of the SOP implies that packaging takes place outside the Drying Room. Other than packaging a few samples at a time, it is unclear what precautions are taken to prevent moisture uptake. The SOP also states that checks are carried out for deficiencies in the packets and in the sealing. It is unclear whether these are visual checks. | Clarify precautions taken to limit moisture uptake (particularly by smaller seeds) during packaging. Specify the checks carried out on container integrity and sealing. | M | Y | 2018-08-03 | Precautions to limit moisture uptake and checks carried out on container integrity and sealing incorporated in the SOP. | Revised SOP | Y | Section 6.1.6.2 (page 22) contains a detailed explanation of how moisture uptake is prevented. Protocol to check the quality in sealing of aluminium pouches and containers is explained on page 22 and Annex 4. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-4 | Procedure | Clause 4.2.4, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "for medium-term storage, samples shall be stored at a temperature of 5-10oC. For samples not stored in sealed foil packets, relative humidity in the storage chamber shall be 15 ± 3 percent" There are concerns over whether the plastic MTS containers are airtight. A collection with 2% oil content dried at 15%RH/15oC would have a predicted moisture content of 6.14% wet basis; at 30%RH/4oC the prediction is that moisture content would rise to 9.69% w.b. This means that if the lids are not airtight, the MTS collections will take up moisture and collections may deteriorate more quickly than expected. | Provide evidence that the containers used for the MTS collection are airtight. | M | Y | 2018-08-03 | Evidence provided in the revised SOP. | Revised SOP | Y | Protocol to check the quality of the containers used in MTS is explained in Annex 4. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-5 | Procedure | Clause 4.4.3, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "at least 50 seeds of the original and subsequent most-original sample shall be archived in long-term storage for reference purposes." The SOP does not describe activities related to preparation and archiving of reference or voucher samples of seed. Furthermore, for ease in viewing the information at a glance, sample preparation for the following activities could be consolidated in a table: LTS, MTS, phytosanitary testing, viability testing, distribution, safety duplication, regeneration and the 50-seed voucher sample. | Include steps in the Conservation SOP describing how many seeds are prepared in the voucher sample (seed file) and where they are stored. A template was provided along with this Finding Report as an example of a consolidated table (see second sheet-tab below). Tailor the table to suit your needs when consolidating your sample preparation activities. Include the table in the SOP. | M | Y | 2018-08-03 | A consolidated table covering information on sample preparation six crop groups is included in the SOP as Table 4. | Revised SOP | Y | Table 4 shows how samples are prepared and stored for ICRISAT's six crops. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-6 | Procedure | Clause 4.3.1, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "the initial seed viability test should be conducted after cleaning and drying the accession or at the latest within 12 months after receipt of the sample at the genebank." The SOP does not include information on the maximum time allowed to elapse prior to conducting viability tests on clean dry seed. | Specify in the Viability Testing section the maximum number of days or months allowed to elapse between receipt of the sample at the genebank and initial viability testing. Clarify if initial viability testing is conducted prior to or after storage. | M | Y | 2018-08-03 | Information on conducting viability tests provided in the SOP. | Revised SOP | Y | Section 6.1.4 contains information regarding the number of months allowed to elapse between receipt of the sample and initial viability testing. Viability testing is conducted prior to storage. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-7 | Procedure | Text, p 33, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "every effort should be made to germinate all viable seeds in a collection using optimum conditions and appropriate dormancy-breaking treatments where needed. Non-germinated seeds remaining at the end of a germination test should be cut-tested to assess whether they are dead or dormant. Seeds with ﬁrm, fresh tissue are likely to be dormant and should be counted as viable seed." The SOP does not adequately describe the methodology used to assess whether non-germinating seed are dead or dormant, the type of lighting used in germination chambers and the precise criterion by which germination is judged, e.g., emergence of a radicle by 2 mm or emergence of both radicle and shoot. | Include an indirect test for viability in the protocols to ensure that non-germinated seeds are actually dead. Examples of indirect viability tests are cut tests or tetrazolium tests. Specify the type of lighting used in germination chambers. Specify the precise criterion by which seedlings are considered as germinated. | M | Y | 2018-08-03 | Methodology describing the germination test included in the SOP. | Revised SOP | Y | Indirect tests are described on page 20. Classification of normal vs. abnormal development is illustrated in Fig. 10. Dormancy breaking treatments are described on page 20 (scarification, light, temperature). | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-8 | Procedure | Text, p 27, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "after drying, all seed samples for long-term storage shall be packaged in a barcode-labelled, vacuum-sealed trilaminate aluminium foil packet." It is unclear how genebank staff ensure that foil packets are properly vacuum-sealed. | Describe the method by which the foil bag sealer is tested to ensure satisfactory sealing. | M | Y | 2018-08-03 | Details to ensure satisfactory sealing incorporated in the SOP. | Revised SOP | Y | Protocol to check the quality in sealing of aluminium pouches and containers is explained on page 22 and Annex 4. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-9 | Procedure | Clause 3.3.16 QMS: Audit Guide and Clause List v1.6 | The QMS Audit Guide and Clause List states that "a monitoring system shall be in place to continuously check seed inventory particularly prior to fulfilling a request. Quantity and weight thresholds that trigger regeneration shall be clearly documented for each accession." Section 6.3.2 describes the monitoring of seed inventory but does not mention quantity thresholds. | In section 6.3.2, specify what the inventory thresholds are for different species. | M | Y | 2018-08-03 | Inventory thresholds for distribution provided in the SOP. | Revised SOP | Y | Quantity thresholds for the six crops are specified in step 6.3.3.2. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-10 | Materials and Equipment | Clause 4.7.2, FAO. 2014. Genebank Standards for PGRFA Genebanks CRP Barcoding Initiative 2016 | The FAO Genebank Standards state that "All data and information generated in the genebank relating to all aspects of conservation and use of the material should be recorded in a suitably designed database." Although improvements have been made regarding centralized databases and barcoding, it appears that there are areas and procedures where data is not captured in databases and barcodes are not used for data retrieval and capture. | State if the genebank captures data and information related to all processes of conservation and use in a central database and makes use of barcoding for data retrieval and capture. Submit a brief update including: 1) a list of areas and procedures in which data is retrieved and captured from a central database and barcodes are used for data retrieval and capture, 2) a list of areas and procedures in which data is not yet directly integrated into a central database and barcodes are not utilized and, 3) the plan to put into operation a central database and implement barcoding in areas, procedures and locations where they are not currently used. | M | Y | 2018-08-03 | Updated the information on barcoding in the SOP. | Revised SOP | Y | An update on capturing data in a database system and barcoding was added to Section 5 (most areas now bar-coded). ICRISAT's deadline to integrate the remaining areas, characterization and accession descriptors is December 2019 (personal communication) | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-11 | Materials and Equipment | QMS-Equipment | The Materials and Equipment section does not state the specifications for barcode labels and ribbons that would withstand the extreme temperature, moisture and light conditions in genebank operations. | Specify in the Materials and Equipment section the type of printers, ribbons (ink) and labels used for barcoding in seed processing, drying, MTS and LTS that are explicitly manufactured to withstand extreme temperatures, moisture and light. | M | Y | 2018-08-03 | Details provided in the Materials and Equipment section of the SOP. | Revised SOP | Y | Printers, ribbons and labels are adequately described in Section 5. | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-12 | Infrastructure and work environment | QMS | The "Infrastructure and Work Environment" section describes area specifications, monitoring of temperature and relative humidity and specific protocols and alarms that safeguard staff and collections. The SOP does not describe the way in which the Center responds to significant threats to the collections such as fire or flooding. | In a Related Document, briefly describe the genebanks 24-hour emergency plan in the event of a significant threat to the collections such as fire or flooding. Include the following: 1) number and type of alarms and emergency equipment currently in place at the genebank and the frequency with which fire alarms are tested, 2) the mechanism by which the alarms are detected and handled (e.g., the fire alarm triggers an audible siren and sends an electronic notification to maintenance crew, genebank manager and key genebank staff), 3) the Centre's list of "First Responders " trained to address the hazards during the day, night or weekends, 4) the frequency with which the 24-hour emergency response is tested. | M | Y | 2018-08-03 | A 24-hour emergency plan – Genebank document included in the SOP | Revised SOP | Y | ICRISAT's 24- hour emergency plan adequately describes alarms, actions and first responders. Alarms and triggers are described and illustrated in the CONS SOP (Section 9). | NA | Finding cleared in Round 1 | 2018-09-28
ICRISAT-2018-CONS-13 | Occupational Health and Safety (OH&S) | QMS | The Occupational Health and Safety section states that activities performed in the Conservation SOP comply with requirements and recommendations in the Centre's Health and Safety Manual. The SOP does not describe specific precautions taken when working in LTS, MTS and drying areas (e.g., maximum time allowed to work in the areas, the use of a buddy-system, etc). | Add text in the OH&S section describing all necessary precautions taken when staff work in LTS, MTS and drying areas including the time allowed to stay in the areas (low temp and dry room conditions), specific precautions taken in the event that a staff member works alone and prevention of cold/heat shock when moving from outside environments to inside conditions and vice versa. Ensure staff familiarity with health and safety measures by evaluating staff knowledge of requirements and recommendations. | M | Y | 2018-08-03 | Information on necessary precautions provided in the SOP. | Revised SOP | Y | Occupational Health and Safety precautions when working under LTS and MTS were added to Section 4. | NA | Finding cleared in Round 1 | 2018-09-28
Recommended | QMS Template | QMS | In quality management systems, there is only one source from which all current documentation is obtained. To prevent the use of outdated and obsolete copies, a footer is added to all key QMS documents informing the user where correct and updated versions may be obtained. ICRISAT's Distribution, Regeneration and Characterization SOPs followed the QMS template and included the footer. The Conservation SOP lacks the "uncontrolled document" footer. | Add the "uncontrolled document" footer to the Conservation SOP. The text is as follows: Electronic and printed versions are uncontrolled except when accessed directly from the ICRISAT genebank website (http://www.icrisat.org/). Users are kindly requested to verify the correct version before use. | R | N |  | Footer added in first page of the SOP. | Revised SOP | ü | Footer has been added to page 1 of the SOP.
Recommended | QMS template | QMS | The Procedure sections in ICRISAT's Distribution, Regeneration and Characterization SOPs includes the numbering of major steps, i.e., every major step in the procedure is numbered. The current version of the Conservation SOP includes numbering of major sections, e.g., seed processing, moisture testing, etc. The steps within each section are not numbered. | To ensure uniformity and ease in editing and auditing, apply numbering consistently throughout ICRISAT SOPs. Number the steps in the Conservation SOP as was done in the Distribution, Regeneration and Characterization SOPs. | R | N |  | Steps numbered for the procedures and other sections of the SOP. | Revised SOP | ü | Steps in Procedure section have been numbered.
Recommended | Procedure | QMS | In section 6.1.1 on page 8, it states that "Contents of each packet are emptied into a labelled tray.... the dryness of seeds is checked for cleaning without damage....". It is unclear how the dryness is checked. | Clarify how dryness is checked when examining the seed sample. | R | N |  | Text revised in the SOP addressing the audit findings and the proposed improvement. | Revised SOP | ü | Additional text was added to clarify how seed moisture/dryness is assessed when cleaning a sample. Seed moisture testing was described in 6.1.2.